## Sheet1
Task | Time(hours) | Task description
Programming
Enviroment SetUp(Unity) | 2H
Generate Player/Controls | 5H | player stats | Control | interaction with environment |  | Hit Points/HP
Enemy Basic Class | 5H | basic stats | shared Controls
Enemy- Types Setup | 15H | indivdual enemy types |  | interaction with player |  |  | Min. 3 Types
Game Menus | 10H | Pause | Options | Intro Menu | Particle System
Unity Animations | 10H | Pl-Movement | Fighting | Enemy Ability
Sound Effects | 2H
Level Background Layout | 1H/Level
Level Basic Layout | 3H/Level | Implementation of level design |  |  |  |  | Min. 5 Levels
Special Terrain Configuration | 1H/Type | [5 empty] | Min 4.Types
Testing/Bugfixing/Code Review | 6H
Animation
Sprite Player | 15 H | Layout concept | Movement | Abilities
Sprite Enemy | 7 H/Type | *3 Enemy Types | Layout concept | Attack Animation
Sprite Level Environment | 5H/Level
Level Design
Level Concept | 5H/Level | Level layout | Gameplay | Enemy Position | Strategic Layout
Level Animation | 1H/Level | Story | Background | Setting
Sound | 1H/Level
Managerial-Other
Team Meetings | 10H/Person
Documentations | 5H/Person | Project Structure Plan |  | Arbeitspakete |  | Presentation
Total | 240 Hours